## Sheet1
Risk Catagories | Risk Numbers | Risks | Description | Probability | Impact | Rate | Migitation /Resolution Techiques
Security Risks | 1 | Network infrastructure Risks | Security risks mainly from hackers and malicious application that attempt to attack and gain control over the network infrastructure of the company. | 2 | 2 | High | Cyber- risk assessment,Risk mapping system, Network access control/ end point security,
| 2 | Operational system Risks | Outdated system , inadequate devices , or improperly installation. Inability to assess an issue and fail to take the right action. Safety Risks such as violation of workplace either mentally or physically | 1 | 2 | Moderate | Good managment system in strategy risk plans , updating operational systems , proper installation , good system interaction systems. Applying safety rules and employees right.
| 3 | Database Security Risks | Unauthorized access to the data, data breaches due to intensional or untensinal exposure of sensitive data, Phishing on trusted look sources with malicious links , SQL injection or adding malicious code by attackers in to database system. | 2 | 3 | Extreme | Data classification that help to identify sensitive data, data eruption that convert the data to unreadable format to mask it from attackers, Data Loss prevention such set up back ups in different location, Practising strong password, anti -malware and , and antivirus
Technical Risks | 4 | Code Issue | Poor quality coding associated with poor technical expertise and rushed work. The issue includes logical errors, bugs, and system deficiencies. | 2 | 1 | Low | Integrating coding standards for developers, frequently testing the code, resolving bugs when they are detected.
| 5 | Project Scope creep | Risks that related with poor team management, project delays,and employee burn outs | 1 | 2 | Moderate | Frequently reviewing the scope Breaking down the project in to manageable section or iterations
Managment Risks | 6 | Productivity Risks | Project scope changes to a completely different structure from its initial scope causes delays and missing expectations | 1 | 1 | Low | Setting a strong goals to motivate the team Planning a well- paced project to avoid burouts and lower stress Practicing a transparent team communication on problems and project details Appointing a team leader who can manage and motivate the team
Note :
Probablity is based on 1 to 5 rates where 1 =Rare, 2=Unlikely, 3=Moderate,4= Likely, 5= certain
Impact is based on 1to 5 rates where 1= Insignificant ,2= Minor, 3= Neutral ,4= Major , 5=Catastropic